## TO DO LIST
# | NEW TASKS |  | COST
1 | 206 وارد - مكتب اداري | DONE | 350 | paid
2 | 206 وارد - مكتب دروس let us first give dourous the software 206 same as idere then later we think about the process between 206 idere and 206 dourous dourous can see sijjel idere but read only and vice versa
3 | 204 صادر - مكتب اداري let s first create the grid of 204 then we think about the link between the 206 idere & 204 idere |  | 100
4 | 304 fax وارد let s just create the grid; later on we think of automating the fax and link it to 206
5 | 404 fax صادر let s just create the grid; later on we think of automating the fax and link it to 206
6 | excel and word for dourous office based on previous database excel and word for tilzim based on excel done for dourous office excel and word for istilem based on excel done for tilzim office
7 | word for tislim مواقع العمل
8 | المكتب الاداري: سجل المستودع للمعاملات المنفذة (محفظة) let s just create the grid; later on we link it to 206 idere
# | sijjel 206 - new features
1 | GRID EXPORT (after filtering) GridViewSpreadExport: export grid after applying filtering to pdf or excel | DONE | 40
2 | user privileges: admin (can do everything) - user (can not change user settings) - visitor (read only) | DONE | 20
3 | dropdown mutiselect | IN PROGRESS | 75
4 | dropdown autocomplete suggestmode.contains | IN PROGRESS | 75
5 | GRID PRINT BUTTON (after filtering)
6 | increase the text height in crystal report
7 | I want to enhance the search contains e.g. مدخل مبنى شوقي if I search for مدخل شوقي I don't find anything
8 | user privileges: admin: can do everything admin for each office: can can do everything in his office user edit: for each office read only: for everything | done | 0
9 | Create a new column called ID (for tracking لتعقب حركة المعاملة) IF(mo2addam = 0, new id sequence, else id=to the id that have ra2em motasalsel = mo2addam) nb: sometimes, we have more than one mo2addam for more details, check excel "sijjel samples - grid type" ; sheet "tracking" NB: ra2em motasalsel will be considered a subID for the ID lines having the same ID, means it is the same معاملة by filtering to an ID you will see حركة المعاملة later on we add an option allowing user to mark an ID as important, so user can receive an altert or email when a sent ID, is received again
10 | create a link to attach files to an ID let s first create a form related to an ID that can be accessed by a click from any line this form will show the different ra2em motasalsel linked to this ID and for each ra2em motasalsel you can: 1. add any file (pdf. word, excel photo ...) using copy paste from the user pc (in a folder on the NAS server automatically named "year-ID-subID" 2. create pdf from scanner (create a click that open the scanner software) 3. create word file using a word template having fixed infos and other infos issued from sijjel 206 (subject, 206 number, issued date ...) and from a data form (the HOD name, the user creating the word file ...)
11 | update software on all the pcs, using 1 click from the server
12 | auto backup sql at 12am everyday
13 | auto create pdf report start the beginning of the year at 12:05am everyday
# | naji fares comments
1 | ping to server should be less than 1ms
2 | fix server IP make the software faster
3 | acronis or northon ghost image